## Blatt1
| >>> Time Table Plan for DBHD 1.4 Nuclear Repository HLW DE/CH in M-V near Glasin / Kröpelin - Version 12.0 from 21.12.2018 >>> | [23 empty] | Your personal notes
| Work-Steps in rough Mile-Stones / Year | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036
1 | Planning, Drawing, Thermod.-Calculation DBHD repository | 2014: Planning DBHD 1.4 Repository | Ing. Goebel + 13.000 ww
2 | Long-Term Safety Case Calculation 1 Mio. yrs. In Comsol | 2019: 1 Mio. yrs. | GRS, VTT, Amphos 21
3 | Probe-Drillings to confirm Geology Maps Information | 2019: Probe-Drillings; 2027: 10 years - for the | only Probe-Core-Drillings
4 | Ordering the Shaft-Boring-Machine SBM / 50 Mio. EUR | 2021: SBM; 2027: 1st DBHD column | SBM Order 50 Mio. EUR
5 | Fabrication of Shaft-Boring-Machine / Herrenknecht AG | 2021: SBM Fabrication | D = 12 m Shaft Drill Techn.
6 | Buying 1 st plot of land with a Municipal Council Decision | 2022: Building land | Municipal Council Decision
7 | 1 Compensation Payment to all residents near building land | 2022: 1 C. Payment | 1 Compensation Payment
8 | Preparation around building site - streets, power, water | 2015: Parallel-Planning; 2022: Preparation | Building site environment
9 | Cable Drum House, Work-Over Rig, Concrete Capacity | 2022: Drilling-Site | Building the drilling site
10 | Test Drilling with SBM into rocksalt until reaching req. depth | 2024: 1 Test Drill | Drilling, Concrete, Ventilation
11 | Local and countrywide Pro/Contra repository debate | 2014: Debate, Local-Conferences, Judicial Review, Building-Permission granted | Prüfung - Baugenehmigung
12 | 1. Repository Location decision by country parliament | 2024: Dicision | Part-Site Decision Parliament
13 | 2 Compensation Payment to all residents near building land | 2024: 2. C. Payment | 2. Kompensations-Zahlung
14 | 740 m / Widening Drill Hole to D= 21,0 m with Chain-Saws | 2026: 21 m | Miner works at +16 °C
15 | 1. Storage Decision for 328 HLW Castor Contianers | 2026: STORAGE | Containers, Concrete, Salt
16 | Closure of Deep Big Hole Disposal 1. Location with Salt | 2027: Closure | salt + mountain pressure
17 | Building back of all above ground plant elements to Zero | [23 empty] | Cornfield or meadow | bar: 2029
18
19 | Probe-Drillings to confirm Geology Maps Information | 2015: Parallel-Planning; 2026: Probe-Drillings | only Probe-Core-Drillings
20 | Buying 2 nd plot of land with a Municipal Council Decision | 2028: Building Land; 2034: 9 years for the | Municipal Council Decision
21 | Compensation Payment to all residents near building land | 2028: C. Payment; 2034: 2 nd DBHD column | 1 Compensation Payment
22 | Preparation around building site - streets, power, water | 2029: Preparation | Building site environment
23 | Cable Drum House, Work-Over Rig, Concrete Capacity | 2029: Driling-Site | Building the drilling site
24 | Drilling with SBM into rocksalt until reaching req. depth | 2030: 2 nd Drill | Drilling, Concrete, Ventilation
25 | Local and countrywide Pro/Contra repository debate | 2014: International Debate, Regional-Conferences, complete Judicial Review, Complete Building-Permission granted | Prüfung - Baugenehmigung
26 | Complete Location Decision by country Parliament | 2031: Decision | Total Location Decision
27 | 740 m / Widening Drill Hole to D= 21,0 m with Chain-Saws | 2032: 21 m | Miner works at +16 °C
28 | Storage of 328 HLW Castor Containers | 2033: STORAGE | Containers, Concrete, Salt
29 | Closure of Deep Big Hole Disposal 2. Location with Salt | 2034: Closure | salt + mountain pressure
30 | Building back of all above ground plant elements to Zero | [23 empty] | Cornfield or meadow | bar: 2036
31
32 | Building No. 3 of 8 DBHD colums
33 | etc., etc., etc. etc. | 2015: The total construction and storage time for nuclear waste DE / CH will last 80 years | then the over 60 year old
34 | building No. 8 from 8 DBHD | 2015: Total investment: EUR 5.95 billion EUR - with many jobs for the people in the region | building problem is solved
35
36 | No Sign - Nothing - Beginning of forgetting
| Realistic Planning- and Building times that are possible | 2015: Draft :; 2017: Dipl.-Ing.; 2019: Volker Goebel; 2025: " Original File "; 2031: DBHD 1.4 repository materials | With best regards